## Notes
Week 6 Assignment
This spreadsheet contains data for the Week 6 Asssignment
The Burn Down Chart Example shows how to do the burn down chart calculations
The Data for Week 6 Assignment is where you create your own Burn Down Chart for use in the Week 6 Assignment
You use your burn down chart in the Week6AssignmentTemplate.docx where there are questions to answer in essay format.

## Burn Down Chart Example
Burn Down Chart Example
1. Assume a sprint is 2 weeks long. Also assume you are at the end of Sprint 1
What is the baseline project finish date? |  |  | 18 weeks | (9 Sprints * 2 Weeks for Sprint)
2. Assume you are at the end of Sprint 9. What is the expected project finish date?
|  |  | 24 weeks | (12 sprints *2)
| A | B | C | D | E | F=B-C+E
| Sprint Number | Product Backlog Points | Completed Points in Sprint | Planned Remaining Product Backlog | New Points | Actual Remaining
| 1 | 250 | 25 | 225 | 10 | 235
| 2 | 235 | 35 | 200 | 8 | 208
| 3 | 208 | 20 | 175 | 13 | 201
| 4 | 201 | 30 | 150 | 5 | 176
| 5 | 176 | 18 | 125 | 21 | 179
| 6 | 179 | 21 | 100 | 0 | 158
| 7 | 158 | 36 | 75 | -13 | 109
| 8 | 109 | 15 | 50 | 5 | 99
| 9 | 99 | 13 | 25 | -21 | 65
| 10 | 65 |  |  |  | 41.3333
| 11 | 41.3333 |  |  |  | 17.6667
| 12 | 17.6667 |  |  |  | -6
| Average Completed Points per Sprint |  | 23.6667

## Data for Week 6 Assignment
Burn Down Chart Exercise
1. Assume a sprint is 2 weeks long. Also assume you are at the end of Sprint 1
What is the baseline project finish date?
2. Assume you are at the end of Sprint 9. What is the expected project finish date?
A | B | C | D=B1-C1*A | E | F=B-C+E
Sprint Number | Product Backlog Points | Completed Points in Sprint | Planned Remaining Product Backlog | New Points | Actual Remaining
1 | 500 | 60 |  | 18 |  | 70 | 5
2 |  | 55 |  | 5 |  | 55 | 26
3 |  | 55 |  | 26 |  | 62 | 10
4 |  | 58 |  | 10 |  | 42 | 21
5 |  | 62 |  | 21 |  | 55 | 0
6 |  | 32 |  | 0 |  | 58 | -21
7 |  | 52 |  | -21 |  | 52 | 13
8 |  | 21 |  | 13 |  | 55 | -21
9 |  | 46 |  | 13 |  | 62
10 |  |  |  | 0
11
12
13
14
15
16
Average Points Completed